NALGA National Championships

Work Plan

| No | Item | Description | Target Start | Target End | Responsible | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Registration records | Use NALGA supplied spreadsheet or for recording all relevant information from entry forms of registrations, with facility for producing a range of reports – e.g. mail outs, competition draws, function attendances, shirt details, name tags, etc. |  |  |  |  |
|  | Budget | Construct budget for event which includes all event costs and income, and fees required to be made by entrants | 18 months prior | 12 months prior |  |  |
|  | Notification to entrants | Notification to all entrants on the final arrangements for the Nationals including specific details for the registration function, presentation dinner, the tournament, grade ratings, dress regulations, motorised carts etc. | One month prior to start date of tournament |  |  |  |
|  | Receipts for entrants | Issuing of receipts to entrants | Ongoing |  |  |  |
| 2 | Championship booklet | Prepare and collate material for the championships booklet including; sponsors, committees, welcome addresses, tournament programme, venues, championship rules, entrants, etc. |  |  |  |  |
|  |  | Look at opportunities for sponsors to contribute to the cost of publication by placing adds in the booklet |  |  |  |  |
|  |  | Compile material and prepare artwork, determine number required and obtain quotations for and organise printing. |  |  |  |  |
| 3 | Match committee | Selection of a match committee to adjudicate on any issues arising during the tournament. Based on previous years there needs to be at least 3 or 4 members including the Tournament Director |  |  |  |  |
|  |  | Prepare check list of daily tasks and arrange for volunteers to assist during championships on a daily basis |  |  |  |  |
|  |  | Do a trial run of the draw using preliminary list of registrations and review and assess with committee |  |  |  |  |
|  |  | Determine cut off date for handicaps for Championship draw |  |  |  |  |
|  |  | Handicaps need to be checked for all players with Golflink numbers so divisions and draw can be finalised |  |  |  |  |
|  |  | Prepare and publish final draw and distribute to players (registration package) and clubs (1 week prior to event) |  |  |  |  |
| 4 | Merchandise – shirts, caps, towels, etc | Decide on logo to be used for the 2009 Nationals. Identify and agree on possible suppliers, Obtain samples, indicative costs and delivery period |  |  |  |  |
|  |  | Agree on styles – players and committees Select supplier, finalise numbers and purchase Suggested colour of the caps be the same light blue as the shirt |  |  |  |  |
| 5 | Main sponsors | Removed – dealt with under other actions |  |  |  |  |
| 6 | Hole sponsors | Determine which sponsors wish to use their own promotion material |  |  |  |  |
|  |  | Prepare placards for holes sponsors |  |  |  |  |
| 7 | Local Gov Grant | Finalise requirements for funding grant |  |  |  |  |
|  |  | Notify of any promotions of the event – invitations to attend |  |  |  |  |
|  |  | Maintenance of records of expenditure against grant |  |  |  |  |
| 8 | Registration packages | Decide what items are to be included in the package (links with items 1, 2 and 4) and what type of bag is to be used |  |  |  |  |
|  |  | Determine numbers required (links with item 1) Purchase or collect items as needed |  |  |  |  |
|  |  | Purchase and prepare name tags for participants |  |  |  |  |
|  |  | Assemble packages, print and attach name tags |  |  |  |  |
| 9 | Raffles | Finalise any raffles to be held during tournament |  |  |  |  |
|  |  | Liaise with NALG re NALGA raffle |  |  |  |  |
| 10 | Golf clubs | Select Golf Clubs | 2 Years Before |  |  |  |
|  |  | Initial deposits if required |  |  |  |  |
|  |  | Finalise arrangements if numbers down or weather prevents play |  |  |  |  |
|  |  | Payment arrangements to clubs |  |  |  |  |
|  |  | Distribution of brochures and entry forms |  |  |  |  |
|  |  | Finalise competition arrangements with each venue including scoring recording and screen viewing, starting arrangements, course set up, final numbers, distribution and collection of cards, need for helpers or spotters |  |  |  |  |
|  |  | Signage requirements |  |  |  |  |
|  |  | Placement and collection of sponsor placards and other promotional material, preparation of check list |  |  |  |  |
|  |  | Arrangements for carts at each course. |  |  |  |  |
| 11 | Prizes & trophies | Identify and review options for major prizes and daily prizes – obtain quotes and time line for supply |  |  |  |  |
|  |  | Agree on prizes to be awarded for specific events – place orders with selected suppliers |  |  |  |  |
|  |  | Arrange for return of perpetual trophies as required – National & ACT Division (National winners to arrange engraving individually ) |  |  |  |  |
|  |  | Daily Prizes – agree on options for prizes, discuss golf products with Clubs |  |  |  |  |
| 12 | Registration function | Prepare Indicative Budget for the function for inclusion in overall budget | 18 months prior |  |  |  |
|  |  | Finalise numbers attending |  |  |  |  |
|  |  | Liaise with venue on arrangements for room/area set up, catering, use of PA, display of sponsor and promotional material, |  |  |  |  |
|  |  | Prepare order of proceedings for the function – welcoming group, distribution of packages, speeches (introductions, competition arrangements) |  |  |  |  |
|  |  | Arrangements for setting up an area for registrations and distribution of the packages (need to establish a team to undertake this) including reception tables |  |  |  |  |
|  |  | Prepare invitations for special guests - total of 44 people invited |  |  |  |  |
|  |  | Prepare lists of entrants for checking registration, recording attendance and receipt of package |  |  |  |  |
|  |  | Set up a room/area for the welcome function |  |  |  |  |
|  |  | Prepare Power Point presentation for acknowledgement of sponsors |  |  |  |  |
|  |  | Arrange MC for Welcome Function |  |  |  |  |
| 13 | Presentation dinner | Prepare Indicative Budget for the event for inclusion in overall budget | 18 months prior |  |  |  |
|  |  | Invitations to guests with RSVP by required deadline |  |  |  |  |
|  |  | Notify caterer and venue management of final numbers attending (links to item 1) and any special dietary requirements |  |  |  |  |
|  |  | Payments to caterer in accordance with schedule |  |  |  |  |
|  |  | Prepare order of proceedings for the function – MC, welcoming group, timing of speeches, food, Flag handover |  |  |  |  |
|  |  | Confirm NALGA protocol requirements – refer rules and regulations for the conduct of the championships – order of prizes |  |  |  |  |
|  |  | Finalise arrangements for an MC |  |  |  |  |
|  |  | Determine seating and table allocations (Championship Rules) |  |  |  |  |
|  |  | Set up sponsorship signage |  |  |  |  |
|  |  | Prepare Power point presentation sponsor acknowledgements |  |  |  |  |
|  |  | Prepare power point presentation with photos of the event |  |  |  |  |
|  |  | Compile and arrange printing of programme (and menu if not done by the caterer) |  |  |  |  |
|  |  | Confirm any AV arrangements |  |  |  |  |
|  |  | Arrangements for transport of all trophies to venue on the afternoon of the dinner |  |  |  |  |
| 14 | Scoring System | Identify procedures for entering data into course system for producing daily results |  |  |  |  |
|  |  | Identify procedures for entering data for 72-hole events using NALGA scoring Template |  |  |  |  |
|  |  | Identify procedures for players to view running scores from day 2 on |  |  |  |  |
|  |  | Procedures for card collection |  |  |  |  |
| 15 | Promotion | Distribution of brochures and entry forms at NALGA Championships | 2 years prior | 12 months prior |  |  |
|  |  | Prepare and send notices and application forms NALGA Website co-ordinator |  |  |  |  |
|  |  | Send notice to all World NALG organisations |  |  |  |  |
|  |  | Arrange for advertisements in relevant publications |  |  |  |  |
|  |  | Press coverage – arrange for articles in Press |  |  |  |  |
| 16 | Accommodation | Approach to be made to accommodation complexes to provide discounts to NALG entrants |  |  |  |  |
|  |  | Include information on NALGA website under the National Championships page |  |  |  |  |

Hole Sponsors

| Hole No | Sponsor | Status | Amount | Hole No | Sponsor | Status | Amount |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 |  |  |  | 10 | Tyre Power | Paid | $500 |
| 2 |  |  |  | 11 | Tradies | Paid | $500 |
| 3 |  |  |  | 12 | K and K Glass | Paid | $500 |
| 4 |  |  |  | 13 | Cox & Partners | Paid | $500 |
| 5 |  |  |  | 14 | Quest Employment | Paid | $500 |
| 6 |  |  |  | 15 | Vacant |  |  |
| 7 |  |  |  | 16 | Vacant |  |  |
| 8 |  |  | $500 | 17 | Vacant |  |  |
| 9 |  |  | $500 | 18 | Vacant |  |  |
| Totals | Paid | $7000 |  |  |  |  |  |